## Key dates
| Key milestones | Sarah | Hilde
April
w/c 4th | Concept and concept linking available to test
w/c 11th
w/c 18th
w/c 25th
May
w/c 2nd
w/c 9th | First response domains available to test
w/c 16th |  |  | On leave
w/c 23rd
w/c 30th |  | Conference 1-3 June
June
w/c 6th June
w/c 13th June |  | On leave
w/c 20th June | Question grids/Access rights to test
w/c 27th June
July
4th July
11th July | R9 QDTs selected | ESS conference
18th July
25th July |  | 3MC conference
August
1st Aug
8th Aug
15th Aug
22nd Aug
29th Aug | Question as instrument available to test
September
5th Sept | Next SERISS WPRB meeting
12th Sept
19th Sept
26th Sept
October
3rd Oct
10th Oct | Questionnaire functionality available
17th Oct
24th Oct